## Log
Shop Drawing Log
for
Sewer and Manhole Rehabilitation
Toms River Municipal Utilities Authority
MC Project No. 15001124A
MC | SPEC. |  | SUBMITTAL |  |  | REVIEWER | REVIEW STATUS
NO. | SEC.# / | DESCRIPTION | DATE | RETURN TO CONTRACTOR |  |  |  | REMARKS | COMPLETED
| DWG# |  | RECEIVED | DATE | ACTION TAKEN
1 | 2602 | Allstate Submittal No. 1 CIPP Liner Designs | 2016-03-24 |  | NET | WTB | GeoKrete substitution submitted and is in review | Submitted to TRMUA for comment Requires More Lollipops Lorem |  | C:\Users\William\PythonScripts\stamps\TEST\production\IN\SD#1 - Quadex Structure Guard.pdf
2a | 2602 | Quadex Cement Coating | 2016-03-24 |  | NET | WTB | GeoKrete substitution submitted and is in review | Lollipops |  | C:\Users\William\PythonScripts\stamps\TEST\production\IN\SD#2 - Quadex Cement coating.pdf
3 | 2602 | Quadex Installation Specs | 2016-03-24 |  | NET | WTB |  |  |  | C:\Users\William\PythonScripts\stamps\TEST\production\IN\SD#2 - Quadex Cement coating.pdf
4 | 2602 | Parson Parsonpoxy FP | 2016-03-24 |  | NET | WTB |  |  |  | C:\Users\William\PythonScripts\stamps\TEST\production\IN\SD#2 - Quadex Cement coating.pdf
5 |  | RS Technik Lateral Resin | 2016-03-24 |  | ET | WTB |  | specifiy which lining is being used |  | C:\Users\William\PythonScripts\stamps\TEST\production\IN\SD#2 - Quadex Cement coating.pdf
6 | 3650 | Avanti AV-100 Chemical Grout | 2016-03-24 |  | NET | WTB |  |  |  | C:\Users\William\PythonScripts\stamps\TEST\production\IN\SD#1 - Quadex Structure Guard.pdf
7 |  | Allstate Submittal No. 1 CIPP Liner Designs | 2016-03-24 |  | NET | WTB |  |  |  | INSERT PATH HERE
8 |  | Allstate Submittal No. 2 Felt Material | 2016-03-24 |  | NET | WTB |  |  | ` | INSERT PATH HERE
9 |  | Allstate Submittal No. 3 Polyester Resin | 2016-03-24 |  | NET | WTB |  | specificy which resin is being used |  | INSERT PATH HERE
10 |  | Allstate Submittal No. 4 Installation & QC | 2016-03-24 |  | NET | WTB |  |  |  | INSERT PATH HERE
11 |  | Allstate Submittal No. 5 Notice to Residents | 2016-03-24 |  | NET | WTB |  |  |  | INSERT PATH HERE
12 |  | Midas Sewer Control Plan | 2016-03-24 |  | NET | WTB |  |  |  | INSERT PATH HERE
13 |  | Geopolymer GeoKrete | 2016-03-24 |  | NET | WTB |  | Proposed substitution for 1&2 |  | INSERT PATH HERE
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
LEGEND
NET - NO EXCEPTION TAKEN
ET - EXCEPTION TAKEN AS NOTED
E & C - NOTE EXCEPTION & CONFIRM IN WRITING
R & R - REVISE & RESUBMIT
REJ - REJECTED
| XX | RE-SUBMITTALS